## Slide 1: Agile Awareness
Agile Essentials Training Pack

## Slide 2: Contents
Aim of this training pack
What is Agile
Agile compared to Waterfall
Types of Agile Methodologies
Scrum Framework and overview
Defining requirements
User Stories and Product Backlog
Estimating
Planning
Developing the Solution
Agile Principles and Agile Myths
Terminology
Useful Links
Other Resources

## Slide 3: Aim of this training pack
The aim of this training is to give you a basic understanding of Agile enabling you to take the Agile Essentials - Awareness Quiz and pass!
All of the information within this training pack has been sourced from various online training, Atos resources and experience.
Further supporting documents can be found at the end of the slides.

## Slide 4: What is Agile?
Agile delivery incorporates a mix of practices and processes to deliver adaptive, incremental and iterative software that supports early business value and low cost change
Agile projects are adaptive - small items of work allow the customer to revisit their requirements and reduce the cost of change
Agile projects are incremental - the code is built over phases meaning working code can be presented to the customer early, realising early business value
Agile projects are iterative - they produce code in small cycles, building on what has been delivered before

## Slide 5: Difference between Scrum and Waterfall
Plan
Build
Test
Review
Deploy
Waterfall
Process always flows down.
Once requirements are defined they cannot be easily revised.
Often a long wait for the customer before they see any deliverables.
Once a step has been passed it is often never revisited.
Agile
Iteration / Sprint
Plan
Review
Iteration / Sprint
Plan
Build
Iteration / Sprint
Plan
Review
Build
Test
Test
Review
Build
Test
Deploy to live
Plan
Iteration / Sprint
Plan
Build
Test
Review
Iteration / Sprint
Plan
Build
Test
Review
Iteration / Sprint
Plan
Build
Test
Review
Deploy to live
Process flows left to right.
Each iteration/sprint produces a part of the deployment for that phase.
Requirements can be revisited before each iteration/sprint to accommodate any changes.
Notes: The main difference between Scrum and Waterfall projects is that Scrum has many small items of work and code is delivered early in the project whereas Waterfall projects do not release any usable code until the very end.

## Slide 6: Types of Agile Methodologies
There are many different types of Agile methodologies but the most frequently used one within Atos is Scrum
Scrum
eXtreme Programming (XP)
Agile Modelling
agileGDP
Kanban
Feature driven development
Agile Unified Process (AUP)
Agile

## Slide 7: Scrum Framework
Release Planning Sprint Planning Design, Develop, Test Delivery & Assessment
Define requirements, plan iterations
Develop the solution
Review and release
Updated Requirements
& Process
Improvements
Requirements are identified for the release and ordered by priority
They are then put into Sprint Backlogs
The finished code is presented to Stakeholders and then released
Code is developed and tested
Release – this is a defined number of Sprints
Sprint – multiple ones form a Release
Notes: This slide provides an overview of the Scrum Framework.

## Slide 8: Scrum Overview
For each Sprint (sometimes called Iterations) there are three main steps
Define requirements, plan iterations
  At the start of an Iteration the items are selected from the Product Backlog based on the Product Owners priorities and how much the team thinks they can complete in the timeframe. They are then put into a Sprint Backlog
Develop the solution
  The Scrum Team focus on completing the items within the Iteration, the scope is fixed for this phase.
Review and release
  The Scrum Team demonstrates the working code to the Stakeholders. Then the team does a Retrospective and discusses how to improve the process.
At the end of a defined set of Iterations the code is deployed to live (this is the end of a Release)

## Slide 9: Defining Requirements
Requirements in Scrum are defined as User Stories and are usually written in the following way
As a (user role), I want (specific feature), so that (benefit realised).
Each User Story is something that is to be developed and tested to enhance the products value
It is important that the Product Owner writes a good User Story so that everyone is clear on the requirements and what they are ultimately trying to produce

## Slide 10: Writing a Good User Story
A useful way of writing a User Story is to remember the following acronym INVEST
Independent – the User Story should be independent, you should be able to work on any User Story from the Product Backlog without having a dependency on another one.
Negotiable – the User Story is not a binding contract but rather the spirit of what is required.
Valuable – the User Story should add some value to the product otherwise it shouldn’t be done.
Estimable – the User Story should be able to be estimated as otherwise it will be difficult to prioritise within the Backlog.
Small – the User Story should be small as it is then more manageable.
Testable – the User Story should be testable to be done, it should be possible to write the acceptance criteria from the User Story.

## Slide 11: Product Backlog
These User Stories then form the Product Backlog each one becoming a Product Backlog Item
During the project, this Product Backlog is maintained by the Product Owner
The team take each item from the Product Backlog and estimate the size of it and its priority.
Priority is usually ‘high’, ‘medium’ and ‘low’
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).

## Slide 12: Estimating in Agile
There are many ways of estimating the size of a Product Backlog Item
The following are a few of the more common ways of estimating within Agile.
  T-shirt sizing – Small, Medium, Large
    Better for earlier on when not much detail is known
    Quick way to produce relative sizing as each item is compared with the others
  Planning Poker
    Ideal for when more detail is known.
    Uses the Fibonacci Scale (1,1,2,3,5,8,13,21…..).
    Each team member sizes the item from the Product Backlog individually and then shared their estimate with the team. If the team have a large disparity between values then the item is discussed and then the vote is taken again.

## Slide 13: Estimating in Agile
  Story Points
    This is the weighting given to each of the items in the Backlog.
    The team take a known item from the Product Backlog and give it a size and number of Story Points and then this is used as a baseline for the rest of the Product Backlog items.
If any of the estimates is large, then it is useful to break the User Story down into smaller items of work as they then become more manageable

## Slide 14: Plan Release
Once the team have prioritised and sized the Product Backlog Items they are able to decide on what is to be released to the customer first.
Usually this will be the highest priority User Stories
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
High
Medium
Low
Product Backlog
3
8
5
1
3
3
2
3
2
8
3
1
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
3
8
1
3
3
2
Release 1
As a (user role),
I want (specific feature),
so that (benefit realised).
5
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
3
2
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
8
3
1
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
3
2
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
8
3
1
As a (user role),
I want (specific feature),
so that (benefit realised).
3
Priority
Size Estimate

## Slide 15: Plan Iterations / Sprints
The User Stories are then split into Sprints/Iterations with the higher ones being worked on first
The Sprint is a set length of time (Timebox) and this will determine how many User Stories can be completed in each one
As a (user role),
I want (specific feature),
so that (benefit realised).
Sprint 1
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
Sprint 2
Sprint 3
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
Release 1
1
8
3
3
3
2
5
1
2
8
3
3
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
3
8
1
3
3
2
Release 1
As a (user role),
I want (specific feature),
so that (benefit realised).
5
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
3
2
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
As a (user role),
I want (specific feature),
so that (benefit realised).
8
3
1

## Slide 16: Timeboxing
Each Sprint within an Agile project is the same fixed period of time, usually 2-4 weeks.
This allows the team to plan how much work can be done in each Sprint as the capacity of the team is constant.
The most important rule in Timeboxing is that the work stops at the end of the timebox and then progress is reviewed
  has the goal been met?
  what progress has been made?
  what changes do we need to make to the plan going forward?
When planning the timeboxes are scheduled in advance to make the team and stakeholders aware of key dates in advance

## Slide 17: Definition of Done
In an Agile project it is important to define when something is determined as done because everyone has a different definition of what is ‘done’
For the Product Backlog the Definition of Done (DoD) is a quality criteria that determines if each item of the Product Backlog is completed or Done.
    It should be generic so it can be applied to all of the User Stories
    It should be agreed by the whole team
    It should be achievable
Defining the definition of done helps to give the team a better understanding of the requirements and ensures the completion conditions are listed
In Scrum everyone is involved with the definition of done

## Slide 18: Roles within Agile Projects
Within an Agile project there is a team that is working towards a common goal
It is important that the team is able to effectively Communicate, Collaborate and Coordinate in order to achieve this goal
Typically an Agile team is made up of the following members
  Product Owner
  Scrum Master
  Scrum Team

## Slide 19: Product Owner
    The Product Owner is the Decider
    Their main roles in an Agile project are
  to own, review and refine the Product Backlog as the project progresses
  provide input into the daily Scrum meetings
  the Product Owner role is often performed by a Business Analyst
    See this YouTube video Agile Product Ownership in a Nutshell for a good understanding of how a Product Owner manages the Stakeholders expectations and the Product Backlog (15 mins)

## Slide 20: Scrum Master
The Scrum Master is the Facilitator
    Their main roles in an Agile project are
  to ensure the Scrum Team work effectively together
  to ensure everyone in the Scrum Team have the tools they need to perform their job
  monitor the progress made
  report on the progress made, this is often done using the Burndown Chart
Here is a quick YouTube video describing the Scrum Master’s role, taken from the Scrum Guide.

## Slide 21: Burndown Chart
The Burndown Chart shows the progress during a Sprint or Release
The chart progresses to zero when all of the work will be completed
There are many ways of tracking the progress but the most simple is in an excel spreadsheet
Chart: Sprint Burndown Chart
| 1 | 2 | 3 | 4 | 6 | 7 | 8 | 9 | 10
Desired | 280 | 252 | 220 | 198 | 165 | 137 | 109 | 78 | 50
The sprint is for 2 weeks (10 days), with total capacity of 280 hours
(4 Team Members x 7 hours a day x 10 days)
Ideal trend line
Effort in Hours
Days in Sprint
Actual effort
remaining

## Slide 22: Scrum Team
The Scrum Team are the Doers
Their main role is to get things done
Scrum Teams are Self Organising Teams which share knowledge and knowhow between them.
Scrum Teams are normally multidisciplinary, with developers, testers and analysts, this is called a Cross-Functional Team. They have all the skills to needed to get the whole job done.

## Slide 23: Self Organising Team
A self organising team is a group of individuals who are working towards a goal, have the ability to make decisions and can adapt to changing requests.
For a self organising team to work effectively they must:
  be suitable for the role they are performing – someone in the wrong role will be demotivated and cause delays as they learn or their mistakes are corrected
  work together as a team and communicate – effective communication is key as members of the team cannot work as individuals for the team to progress
  trust each other and respect each others roles within the team
To help a team succeed they should also be motivated.

## Slide 24: Develop The Solution
When developing the solution within an Agile project, there are a number of key practices that are followed:
Automation – automate as much as possible! We automate tasks within an Agile project as they are often repeated again and again and again and again….
  Continuous Integration – code is continually integrated into the existing product (build) and tested to ensure it integrates. This allows the quality of the build to be maintained and reduces risk of large pieces of code being deployed
  Automated Testing – helps to reduce risk and manual effort and gives early feedback on the quality of the product being developed. This can be used for
    unit testing
    integration testing
    functional testing
    user story testing

## Slide 25: Develop the Solution
Build Quality In – developers are responsible for producing code that works and could be released to production. This can be achieved by
  Collaboration among the developers
    The best code comes from teams of developers who collaborate regularly to discuss the best ways to build the system and check each other’s work
    eXtreme Programming (XP) values collaboration so highly it established Pair Programming as a practice to be used for all technical work
  Continuous testing
    Agile methods expect developers to be testing their code as they write it.
    Test Driven Development (TDD) is where the developer writes the tests before writing the code. This helps with a better design and better code as the developer is focused on what could go wrong
  Refactoring of the code
    This refers to redesigning the code after it has been implemented if it is discovered that the initial design is no longer going to work

## Slide 26: Develop the Solution
Technical Debt – this can be thought of as work that needs to be done before an item is ready to be released. Technical Debt can be introduced in a number of ways
    We develop just enough to get the item released and then revisit the code at a later date
    The developers don’t have the required knowledge to write the code correctly
    Pressure from the business to release code that isn’t ready
    Lack of collaboration amongst the development team
    Lack of alignment to industry standards or best practices
  Technical Debt must be managed by avoiding shortcuts, using simple design and refactoring regularly.
Product Design – the design of an Agile solution is simple and intelligent. It is fit for purpose without being complex. As the project progresses, the design may be altered to meet the required solution.

## Slide 27: Develop the Solution
Software Changes – any change that is to be made to the code should be evaluated first
  does it have a clear purpose
  will the change have an impact on the technical debt
  This also applies to bug fixing. Fixing the bugs should be prioritised against the value they will bring to the product.

## Slide 28: DevOps
what is DevOps? – this is a collaborative approach to software development that characterises mature agile delivery. The purpose is to minimise the time and resources taken to deliver software.
There is a strong overlap with Agile although it can also be used within a more traditional structure.
DevOps uses the following foundations:
  Adopting Kaizen philosophy
  Cost / benefit analysis
  Automation
  Systems thinking / Collaboration
Chris Baynham-Hughes has done an overview video which explains more about DevOps (17 mins)

## Slide 29: Stand Up / Daily Scrum
Daily scrum meetings are where the team discuss
  what they have done
  what they are doing
  what they plan to do
  any blockers that they have to their progress
Any blocker that the team identify should be given an owner so that a resolution is found and actions can be taken
A Daily-Stand up should be timeboxed to ensure that the main actions are focused on, normally this is around 15 minutes.
The meeting should follow a structure so that everything can be discussed that needs to be and the focus of the meeting is not lost.

## Slide 30: Stand Up / Daily Scrum
There are a couple of ways a Daily Stand up can be structured
The stand up is held around the teams progress board and progress is updated
The focus of the meeting can be
driven by the items on the board with the high priority, almost completed items being discussed (Board Driven)
or everyone in the team takes a turn to talk about what they have done and are doing (Round Robin)

## Slide 31: Review and Release
There are two types of reviews at the end of a Sprint
Sprint Review – this is where the items developed during the Sprint are reviewed with the team and the Stakeholders.
Sprint Retrospective – this is an opportunity for the team to review what they have done and what they can do better for the next Sprint.

## Slide 32: Sprint Review
The Sprint Review is led by the Product Owner
The review should include the following:
  The Product Owner reviews what has been done in the Sprint and what has not been done
  The Development team discuss what went well and any problems that they overcame
  The Development team demonstrate what has been produced during the Sprint and collate any feedback
  The Product Owner discusses the Product Backlog as it currently stands
  The entire group decides upon the next items to focus on
At the end of the Sprint Review there will be a revised Product Backlog which will indicate what is to be focused on for the next Sprint.

## Slide 33: Sprint Retrospective
At the end of a sprint it is important to review what went well and what could be improved
Everyone should attend the Sprint Retrospective
The Scrum Master facilitates the meeting
The focus is on
  people
  interactions
  processes
  blockers
  tools
  rather than directly on the work itself

## Slide 34: Sprint Retrospective - Structure
Sprint Retrospectives can be structured in a number of ways but the most common is as follows:
The Scrum Master will ask the team to review the improvements that were made following the last Sprint Retrospective. Any that worked well can be incorporated into the way of working, any that didn’t can be discarded or adapted.
The whole team then moves on to review the current Sprint
  Data is collected about the Sprint - this could be everyone writing on whiteboards or sticky notes or even a scribe writing down everyone’s thoughts. Different techniques are discussed on the next slide
End the Retrospective
  At the end of the Retrospective the team will have a list of things that went well and also some improvements. These will be trialled and then reviewed again before being incorporated into the way of working.

## Slide 35: Sprint Retrospective - Techniques
There are a number of techniques for reviewing Sprints.
Mad, Sad, Glad – three areas representing:
  Mad – things that have annoyed the team
  Sad – this that the team don’t think worked as well as they had hoped
  Glad – things that have made the team happy
The Sail Boat – a picture of a boat representing:
  Sails or engines – things that are pushing the team towards their goals
  Anchors – things that are blocking or impeding the team from reaching their goals
The Wheel or Starfish - five sections representing:
  Start - What can we start doing to help our progress?
  Stop - What can we stop doing that is stopping or progress?
  Keep Doing - What can we keep doing because it is helping our progress?
  More Of - What is currently helping our progress that we can do more of?
  Less Of - What is currently blocking our progress and we can do less of?

## Slide 36: Agile Manifesto
The Agile Manifesto was written by a group of independent-minded practitioners of several programming methodologies where they agreed four main values and twelve principles
We are uncovering better ways of developing software by doing it and helping others do it. Through this work we have come to value:
      Individuals and interactions over processes and tools
      Working software over comprehensive documentation
      Customer collaboration over contract negotiation
      Responding to change over following a plan
That is, while there is value in the items on the right, we value the items on the left more.

## Slide 37: Agile Manifesto Principles
The Agile Manifesto follows these principles
Our highest priority is to satisfy the customer through early and continuous delivery of valuable software.
Welcome changing requirements, even late in development. Agile processes harness change for the customer's competitive advantage.
Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter timescale.
Business people and developers must work together daily throughout the project.
Build projects around motivated individuals. Give them the environment and support they need, and trust them to get the job done.

## Slide 38: Agile Manifesto Principles (continued…)
The most efficient and effective method of conveying information to and within a development team is face-to-face conversation.
Working software is the primary measure of progress.
Agile processes promote sustainable development. The sponsors, developers, and users should be able to maintain a constant pace indefinitely.
Continuous attention to technical excellence and good design enhances agility.
Simplicity, the art of maximizing the amount of work not done, is essential.
The best architectures, requirements, and designs emerge from self-organizing teams.
At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behavior accordingly.

## Slide 39: Agile Myths
Agile means you never have to write documentation
  False: documentation is required but it is done as the project progresses and therefore requires less rework.
Agile means I can change my mind whenever I want to
  False: there needs to be some stability, during sprints requirements are on hold.
Agile works on all sizes of projects.
  True: although agile teams should be small so for a large project many small teams may be required to work and then link together.
Agile means teams cannot be controlled by management
  False: agile is controlled by planning, monitoring and adapting.
Agile requires detailed architecture and design
  False: architecture and design are an output of an agile process and are subject to change.
Agile is just the latest hype
  False: agile has been used for many years and more companies are moving towards using it.
Agile is only used for mission critical projects
  False: agile works for all types of projects.

## Slide 40: Recap - Terminology
Product Backlog – this is an ordered list of work that is to be done that will create and maintain the product. It is owned by the Product Owner.
Sprint / Iteration – is a timeboxed period of where a number of User Stories are completed.
User Stories – These are the user’s requirements written as As a (user role), I want (specific feature), so that (benefit realised).
Definition of Done (DoD) - is a quality criteria that determines if each item of the Product Backlog is completed or Done.

## Slide 41: Further Training and Resources
Online Training
  Agile Awareness Certification
    In ‘My Learning’ search for Agile Awareness: 00270305
Books
  Lean from the Trenches
  Kanban and Scrum - Making the Most of Both
  Scrum and XP from the Trenches - 2nd Edition
  Scrum: a Breathtakingly Brief and Agile Introduction
  The Elements of Scrum
Videos
  Scrum in 10 minutes – a short fast paced video to give you an overview of Scrum
  Scrum Training Series – a selection of videos covering areas of Scrum with quizzes at the end

## Slide 42: Useful Links
http://scrum.org
  Their mission is to improve the profession of Software Development.
  The website gives information about Scrum, links to useful resources and training material.
  There are also open assessments that you can take to test your knowledge around the different areas of Scrum.
http://www.scrumguides.org
  This website provides a guide to Scrum written by Jeff Sutherland and Ken Schwaber who developed Scrum.
https://www.scrumalliance.org
  This is a membership organisation that encourages and supports the use of Scrum. It has many useful resources and links to other areas of interest.

## Slide 43: Scrum and Agile on BlueKiwi
Agile Product Owners
Atos Agile Certification Framework

## Slide 44: Thanks
For more information please contact: T+ 33 1 98765432 F+ 33 1 88888888 M+ 33 6 44445678 firstname.lastname@atos.net